## Sheet1
Plan for Building a CI/CD Pipeline Project
Week | CI-CD pipeline project
2023-02-01 | Project Planning | Estimated Houres | Weekly plan
2023-02-08 | Create Github repo | 4 | 1-Create repo 2-Uoload project files 2-Create make file 3-Create requirement.txt
2023-02-15 | Set up clous shell enviroment | 4 | 1-Create python virtual enviroment 2-Create project scrypt test file and test file
2020-02-22 | Enable Github Actions | 2 | Verify Remote Tests pass
2/29/2023 | Authorize Azure app service | 4 | 1-Upload flask files to the repo 2-Create Azure web app
2023-03-05 | Enable continous diploiment with azure pipeline | 4 | 1-integrate CI 2-integrate CD
2023-03-12 | Deploy Flask ML | 2 | 1-deploy initial version
2023-03-19 | New featur | TBD | TBD
2023-03-26 | Get feed back and develop the app | TBD | TBD
2023-04-03
2023-04-10
2023-04-17
| Goals |  | Goals
Python-based machine learning application using the Flask web framework
performing both Continuous Integration and Continuous Delivery

## Yearly Plan
Yearly Plan 2023 for Building a CI/CD Pipeline Project
Quarter | Phase | Backend | CI/CD | Quality
Q1-2023 | Setup GitHub Repo | CI core functionallity using GitHub | CI using GitHub Actions | Validate CI Process
Q2-2023 | Setup Azure CLI environment | Manual Integration & Deplyment using Azure CLI | No automation | Validate API
Q3-2023 | Setup automated CI/CD | CI/CD using Azure pipeline | Cloud-native CI/CD for Azure | Validate CI/CD
Q4-2023 | Documentation | GitHub README.md | No automation
|  | Goals | Goals | Goals

## Quarterly Plan
Plan for Setup GitHub Repo
Week | Backend | CI/CD | Quality
2023-01-02 | Create GitHub Repo
2023-01-15 | Add python files, MakeFile and requirments
2023-03-01 | Invoke Github Action | Setup CI Build Server (GitHub Actions) | Build successfully
| Goals | Goals | Goals
| Providing GitHub Repo | Automated CI using GitHub | Test passed
Plan for Setup Azure CLI environment
Week | Backend | CI/CD | Quality
2023-04-01 | Create and activated python environment | No automation
2023-04-10 | Connect with Github repo and pull the project |  | Validate local repo
2023-04-20 | Intializing Azure environment by invoking make all script and run Flask |  | Validate local Env
2023-05-20 | Implement Test locally by invoking make_prediction.sh |  | Validate API tests locally
2023-06-01 | Creating Azure app service
2023-06-15 | Implement Test for web app by invoking make_prediction_azure.sh |  | Validate App locally
| Goals | Goals | Goals
| Azure local Env is Avaliable |  | Azure Local Env is valid
Setup automated CI/CD
Week | Backend | CI/CD | Quality
2023-07-01 | Create Azure DevOps organization
2023-07-10 | Create puplic poject connected to GitHub Repo
2023-07-20 | Create Azure pipeline |  | modify yaml file according our propriet parameters for build and deploy stage
2023-08-01 | Create linux vm as agent contains docker for build and deploy | Setup Cloud-native CI/CD (Azure Pipeline) | VM is ready to be added as agent to Azure pipeline project pool
2023-08-15 | Run pipeline to build , test pulled code from Github repo and deploy artifcate to Azure app using vm as agent
2023-09-10 | Implement testing pipeline by change application name and push to GitHub |  | Validate pipeline
2023-09-20 | Implement load test using locust |  | Validate API after deployment app by pipeline
| Goals | Goals | Goals
| API available on local Azure | CI is automated | Tests passed
| App avaliable on local Azure app sevice | CD is automated
Deployed on Azure
Documentation
Week | Backend | CI/CD | Quality
2023-10-01 | Implement Documentation for CI/CD project by update README.md | No automation | README.md is clear
| Goals | Goals | Goals
| build A-Z help describes project steps |  | Validate Documentation